Galway SD Action Plan for the Implementation of Individual Career and Academic Plans

| Spring 2010 | Fall 2010 | Spring 2011 | Fall 2011 |
| --- | --- | --- | --- |
| ICAP Trainings Meetings with area counselors regarding alignment of ICAPs within the Arkansas Valley | Present initial information to school board 2.02(1)(b) Identify members of ICAP Design Team (including plans for meetings, updates to administrators, leadership team(s) and school board) Send Action Plan to Colorado Department of Education by 9/3/10 deadline 2.01(1)(a) Develop grade level activities and appropriate guideways using collegein colorado.org Develop timeline for grade level activities Develop plan for annual review of student ICAPs by parents Identify staff roles and begin training staff on implementation of activities Continue to meet with area counselors as plans develop and expand Professional Development as offered by CIC, CCCS and OJC 2.01(1)(b) Students’ academic progress and understanding of financial aid impact tracked by counselor Article in school newsletter and website for parents regarding ICAP description and progress Financial Aid presentation by Otero Junior College representative to parents of 11th and 12th grade parents | Review effectiveness of Senior Seminar Presentations to faculty Professional Development as offered by CIC, CCCS and OJC 2.02(1)(k) Align activities with ASCA standards Final review of implementation plan and grade level activities by administration, leadership team(s) and school board All 6th through 12th grade students will have registered with collegeincolorado.org 2.01(1)(b) Students’ academic progress and understanding of financial aid impact tracked by counselor Pilot activities at various grade levels, revise as needed Financial Aid application assistance at Otero Junior College for parents of 12th grade students | Full implementation of grade level activities (career exploration, post-secondary & workforce goal with yearly benchmarks, interest surveys completed, anticipated major of study) 2.01(2)(b) Each student in 9th through 12th grade will have begun an ICAP portfolio in collegeincolorado.org 2.01 (2)(b) Each student in 9th through 12th grade will have a plan of study printed and kept in permanent records folder Pre-assessments to track and evaluate effectiveness of activities at each grade level Professional Development as offered by CIC, CCCS and OJC 2.01(1)(b) Students’ academic progress and understanding of financial aid impact tracked by counselor Update progress to administration, leadership team(s) and school board Meet with 11th and 12th grade students individually with parent(s)/guardian(s) to review plan of study, progress of portfolio, postsecondary goal Financial Aid presentation by Otero Junior College representative to parents of 11th and 12th grade parents |